## Sheet1
User Stories | Details | Estimated time | Epic
[Setup] | Set up boiler plate React (Gatsby) + Node + MongoDB | 2
[Load one product from server to client] | * client: /products: load an object {productName: 'Name'} from Node server to React app | 1
[Design DB - determine columns so that won't have to fix too much later] | * DB: product table (id, price, quantity, image) | 1
[Load one product from DB to client] | * client: load text (product name) from DB to page * server: load product name from DB into an object through server | 1
[Push one product from server to DB] | * server: push {productName: 'a'} to DB | 1
[Submit new product from client to DB through server] | * client: /admin: Add button to submit + send POST request from client | 1
[Implement user authentication without DB] |  | 1
[Authentication with DB] |  | 1
[Client loads multiple products from DB] |  | 0.5 | (Now we have a website where admin can login to /admin and can add products (object) to DB and client loads them on page /products)
[Add products with multiple fields {name, price, description} (without img)] |  | 1
[Admin add products with multiple fields using a form] |  | 1
[Display products to admin page] |  | 0.5
[Delete products in DB from server] |  | 1
[Delete products from /admin page] |  | 1
[Edit products in DB from server] |  | 1
[Edit products in DB from /admin page] |  | 1.5
[Add product image] |  | 1 | (Now we have a website where admin can login to /admin and can add/edit/delete products to DB and client loads them on page /products)
[Admin edit user and password info] |  | 2
[Detail popup / detail page with add to cart button + quantity +/-] |  | 2
[Set up state management on client and define states] |  | 2
[Update Redux store's state when click add to cart] |  | 1
[Show products with quantity in /cart] |  | 2 | (On client, now user can add products with quantity to cart see them in /cart)
[Display quantity button +/- in /cart] |  | 1
[Update cart state when user clicking on quantity +/-] |  | 1 | (On client, now user can update quantity and remove (when qty=0 show Remove) products from cart in /cart)
[Display user info form + Checkout btn] |  | 1
[Display confirm popup] |  | 1
[Generate unique order id] |  | 0.5 | (On client /products, now user can checkout and is shown a popup message: "Admin will call you in 12h and ship to ur address (COD)")
(On client /products, now we have skeleton loading for the products) [EXTRA]
(On client /products, now there's pagination for products) [EXTRA]
(On client /products, there are now sidebar displaying different categories) [EXTRA]
(On client /products, user can sort by name, price, category) [EXTRA]
(On client /products, user can search for product name) [EXTRA]
[Set up html skeleton for navbar and footer] |  | 1
[Set up html skeleton for all sections] |  | 1
[Style hero] |  | 3
[Style How it works] |  | 5
[Style Products (see more)] |  | 3 | (Style /home)
[Style product list in /products] |  | 3 | (Style /products)
[Style product list in /cart] |  | 3
[Style form] |  | 3
[Style btns] |  | 2 | (Style /cart)
[Style navbar] |  | 3
[Style footer] |  | 3 | (Style navbar and footer)
[Style login page + login form] |  | 3 | (Style /admin login)
[Style product list + style add,edit, delete buttons + style popup add/edit] |  | 4 | (Style /admin)
[Style edit profile page] |  | 3
(Add messenger chat + styling) [EXTRA]
(Add dark mode) [EXTRA]
(The other 99%) |  | 14
85